## Concept
Tank battle is an open-world head-to-head tank combat game.
The terrain will be used for tactical advantage
The focus will be on flow and fell

## Rules
You can move anywhere in the terrain, which is surrounded by mountains
Both players start with finite health and ammo
Each direct hit takes away health
The last player standing wins

## Requirements
SFX : | Gun firing, explosion, barrel moving, turret moving, engine sound.
Static Mesh : | Simple tank comprising tracks, body, turret and barrel.
Textures : | Later-on we´ll want to add for visual flares.
Music : | Background music to create tension.

## Stories
Sprint | Who | Story | Estimate | Realized Points
1 |  | 2017-11-20 | 8 | 0
|  | Setting up subversion repository | 1
|  | Build a world | 3
|  | Build a tank | 1
Make controls for tanks
Make a player 2 (AI, human player)
|  | Make basic userinterface | 3
2 |  | 2017-12-04 | 8 | 0
5
3
3 |  | 2017-12-18 | 0 | 0
4 |  | 2018-01-01 | 0 | 0
5 |  | 2018-01-15 | 0 | 0
6 |  | 2018-01-29 | 0 | 0
Release | ED | 2018-02-05
|  | Total | 16
|  | Completed | 0
|  | Remaining | 16
|  | % Complete | 0%
|  | Avg Velocity | 0
|  | Estimated # Iterations Remaining | #DIV/0!
Parking Lot
|  | Nice to have story #1 | 3
|  | Nice to have story #2 | 5
Dropped
|  | Stuff we didn't need #1 | 6
Stuff we didn't need #2

## Sprint Data
| 2017-11-20 | 2017-12-04 | 2017-12-18 | 2018-01-01 | 2018-01-15 | 2018-01-29
| 1 | 2 | 3 | 4 | 5 | 6
Total Effort | 16 | 16 | 16 | 16 | 16 | 16
Velocity | 0 | 0 | 0 | 0 | 0 | 0
Remaining | 16 | 16 | 16 | 16 | 16 | 16
Completed | 0 | 0 | 0 | 0 | 0 | 0
% complete | bar: 2017-11-20 to 2018-01-29